## table-1c22b31d-9a43-4453-9374-6
Task ID | Task Name | Assignee | Repository | Due Date | Status | Dependencies | Notes | Gitlab
T001 | Setup Airbyte in development | Adam K | IAC | 2025-06-06 | In Progress | N/A | Adam K is working on the setup to create this the right way not a POC based installation | IAC-327
T002 | Determine CD pipeline process for managing airbyte configuration | Chris/Jeff | Data/Airbyte |  | Not Started | N/A | Manage configuration in git and apply via the Airbyte API?
T003 | Get Upscript credentials | Upscript Health | N/A | 2025-06-10 | In Progress | N/A | Waiting on temporary credentials to be able to test generic API
T004 | Upscript to completed Custom API | Upscript Health | N/A | 2025-06-27 | Not Started | Sprint Planning | 2-3 weeks out from last call on 6/3/2025
T005 | Build Airbyte Source | Chris Ferreira | Data/Airbyte | 2025-06-12 | Blocked | T003, T001 | Upscripts to provide credentials to Data API. We can build locally in docker until IAC-327 is completed
T006 | Build Airbyte Destination | Chris Ferreira | Data/Airbyte | 2025-06-20 | Blocked | T008, T001 | Determine credentials to access API
T007 | Build transformations to land data | Chris Ferreira | Data/Airbyte | 2025-06-18 | Blocked | T008, T001
T008 | Build destination API and Database Tables for Pre-Registration Data | Jon/Jake | twiist backend |  | Not Started | N/A
T009 | Update Patient Creation/Change event to add LeadSource | Jon/Jake | twiist backend |  | Not Started | N/A | Add new attribute to DB and API Payload for MuleSoft. Backfill all existing account with LeadSource of "twiist Portal"
T010 | Email generation for pre-registration link |  | twiist backend |  | Not Started | T008 | Send email to the potential PwD to claim account
T011 | pre-registration verification process and frontend changes |  | twiist frontend |  | Not Started |  | Design out the process to verify a user (ask for DOB) to verify against known data
T012 | Changes to fill in fields that can be prepopulated |  | twiist frontend |  | Not Started
T013 | Do Something | Chris | N/A